## Summary
SECURE Quarterly Budget Report
FY 2016-17: 4th Quarter
Multi-County Expenditures | Jul-Jun 2017 Actuals | FY 2016-17 Projection | Remaining Balance
OC Labor Costs | 605270 | 605270 | 0
LA County Software Maintenance | 770000 | 770000 | 0
Professional Services | 42533 | 42533 | 0
Total Labor | 1417803 | 1417803 | 0
OC Project Admin Costs | 1389 | 1389 | 0
Meetings, Inspection, Travel | 1621 | 1621 | 0
Digital Tokens | 0 | 0 | 0
Total Admin | 3010 | 3010 | 0
SouthTech Software Development | 0 | 0 | 0
LA County Software Development | 0 | 0 | 0
Total Development | 0 | 0 | 0
OC Data Center Charges | 15357 | 15357 | 0
Software & Maintenance | 115972 | 115972 | 0
Hardware & Maintenance | 20642 | 20642 | 0
Total Software & Hardware | 151971 | 151971 | 0
Total Project Expenditures | 1572784 | 1572784 | 0
Contract Revenues | Jul-Jun 2017 Actuals | FY 2016-17 Projection | Remaining Balance
1. Orange County | 292500 | 292500 | 0
2. Los Angeles County | 292500 | 292500 | 0
3. Riverside County | 292500 | 292500 | 0
4. San Diego County | 292500 | 292500 | 0
Total Owners | 1170000 | 1170000 | 0
1. Santa Barbara County | 10000 | 10000 | 0
2. Sacramento County | 50000 | 50000 | 0
3. San Mateo County | 25000 | 25000 | 0
4. Ventura County | 25000 | 25000 | 0
5. Marin County | 10000 | 10000 | 0
6. Tulare County | 0 | 0 | 0
Total Partners | 120000 | 120000 | 0
Digital Tokens over Qty 2 | 2600 | 2600 | 0
Meeting Reimbursement | 884 | 884 | 0
Total Project Revenue | 1293484 | 1293484 | 0
Difference | -279300 | -279300 | 0
Additional Cost Per Owner |  | -69825

## Labor Cost
SECURE: OC Labor Cost Summary
FY 2016-17 4th Quarter: Actuals through June 2017
[8 empty] | Actual | Annual
[6 empty] | 89.27% | 10% | Jul-Jun 2017 | Projection
Job # | Name | YTD Lab Hours | Hours Distribution |  | YTD Labor | YTD Labor Burden | YTD Overhead | YTD Total | Budget Total | Labor Distribution
PCR302 | SECURE: Development/Enhancement | 1357.75 |  | 15.29% | 55676.06 | 43306.44 | 5567.63 | 104550.13 | 104550.13 |  | 17.27%
PCR303 | SECURE: Maintenance | 2631.74 |  | 29.64% | 103253.58 | 80630.76 | 10325.45 | 194209.79 | 194209.79 |  | 32.09%
| Development/Maintenance | 3989.49 |  | 44.93% | 158929.64 | 123937.2 | 15893.08 | 298759.92 | 298759.92 |  | 49.36%
PCR304 | SECURE: Support/Help Desk/Admin: Owners | 515.5 | 5.806% |  | 18882.52 | 16749.47 | 1888.35 | 37520.34 | 37520.34 | 6.199%
PCR305 | SECURE: Support/Help Desk/Admin: Partners | 197.75 | 2.227% |  | 6533.79 | 5832.74 | 653.43 | 13019.96 | 13019.96 | 2.151%
PCR306 | SECURE: Support/Help Desk/Admin: Submitters | 3002.5 | 33.82% |  | 81451.22 | 72238.29 | 8127.54 | 161817.05 | 161817.05 | 26.73%
PCR325 | SECURE: Support Costs | 14 | 0.1577% |  | 729.54 | 651.26 | 72.95 | 1453.75 | 1453.75 | 0.2402%
| Support/Help Desk/Admin | 3729.75 | 42.01% |  | 107597.07 | 95471.76 | 10742.27 | 213811.1 | 213811.1 | 35.32%
PCR307 | SECURE: Meetings: Owners | 267 | 3.007% |  | 13817.5 | 12334.87 | 1381.76 | 27534.13 | 27534.13 | 4.549%
PCR308 | SECURE: Meetings: Partners | 237 | 2.669% |  | 10993.1 | 9813.54 | 1099.33 | 21905.97 | 21905.97 | 3.619%
PCR309 | SECURE: Meetings: Submitters | 24 | 0.2703% |  | 706.25 | 630.47 | 70.62 | 1407.34 | 1407.34 | 0.2325%
| Meetings | 528 | 5.947% |  | 25516.85 | 22778.88 | 2551.71 | 50847.44 | 50847.44 | 8.401%
PCR310 | SECURE: Setup/Training: Owners | 5 | 0.05631% |  | 119.8 | 106.95 | 11.98 | 238.73 | 238.73 | 0.03944%
PCR311 | SECURE: Setup/Training: Partners | 64 | 0.7208% |  | 2790.71 | 2491.27 | 279.13 | 5561.11 | 5561.11 | 0.9188%
PCR312 | SECURE: Setup/Training: Submitters | 562.5 | 6.335% |  | 18163.58 | 16072.01 | 1816.4 | 36051.99 | 36051.99 | 5.956%
| Setup/Training | 631.5 | 7.112% |  | 21074.09 | 18670.23 | 2107.51 | 41851.83 | 41851.83 | 6.915%
| Owners |  |  | 9.027% |  |  |  |  | 65293.2 |  | 11.03%
| Partners |  |  | 5.617% |  |  |  |  | 40487.04 |  | 6.689%
| Submitters |  |  | 40.42% |  |  |  |  | 199276.38 |  | 32.92%
| Admin | 4889.25 |  | 55.07% | 154188.01 | 136920.87 | 15401.49 | 306510.37 | 305056.62 |  | 50.64%
| Total | 8878.74 |  | 100% | 313117.65 | 260858.07 | 31294.57 | 605270.29 | 605270.29 |  | 100%

## Labor Hours
Sum of Hours Worked |  |  |  | Employee Name
Job Number | Job Number Description | Years | Month | CHAUDHRY, ZAFAR I | CHENG, TAOJAN | COPLAND, PATRICK A | CORTEZ AGUILAR, VICTOR E | DESAI, MANOJ J | GARCIA, MARIELENA V | JOHNSON, BRETT A | LUU, HOWARD M | MORENO, VERONICA | STECKLER, ADAM T | SUAZO, LUZ M | SULLIVAN, SUSIE Q | TRAN, MATTHEW K | Grand Total
PCR302 | SECURE: Development/Enhancement | 2016 | Jun | 12 | 27.5 | 0.5 | 3 |  |  |  |  | 0.5 |  |  | 9 |  | 52.5
|  |  | Jul | 12 | 57 | 11 | 3 |  |  |  | 16 | 2.5 |  | 5 |  |  | 106.5
|  |  | Aug | 24 | 55.5 | 9 | 5 |  |  |  | 5 |  |  | 35.75 |  |  | 134.25
|  |  | Sep | 32.5 | 67 | 9.5 | 3.5 |  |  |  | 24 |  |  | 22 |  |  | 158.5
|  |  | Oct | 24 | 52 | 4.5 |  |  |  |  | 9 |  |  | 6 |  |  | 95.5
|  |  | Nov | 17 | 39 | 9 | 4 |  |  |  | 12 |  |  | 14 |  |  | 95
|  |  | Dec | 21.5 | 55 | 3.5 | 1 |  |  |  | 13 |  |  | 11 |  |  | 105
|  | 2017 | Jan | 13 | 48 | 9 |  |  |  |  | 14 |  |  | 33 |  |  | 117
|  |  | Feb | 18 | 31.5 | 3 |  |  |  |  | 4.5 |  |  | 6 |  |  | 63
|  |  | Mar | 29 | 58.5 | 14 | [7 empty] | 18.5 |  |  | 120
|  |  | Apr | 29 | 24.5 | 13.5 | [10 empty] | 67
|  |  | May | 27.5 | 55.5 | 14.5 | [7 empty] | 55 |  |  | 152.5
|  |  | Jun | 10 | 54 | 15 | [7 empty] | 12 |  |  | 91
PCR302 Total |  |  |  | 269.5 | 625 | 116 | 19.5 |  |  |  | 97.5 | 3 |  | 218.25 | 9 |  | 1357.75
PCR303 | SECURE: Maintenance | 2016 | Jun |  | 38.5 | 6.5 | 3 | [8 empty] | 2 | 50
|  |  | Jul |  | 53 | 13 | 4 |  |  |  |  | 6 |  | 9 | 4 |  | 89
|  |  | Aug |  | 78.5 | 26 | 8 | [7 empty] | 17 |  | 129.5
|  |  | Sep |  | 102.5 | 47.5 | 98.5 |  |  | 2 |  |  |  | 2 | 29.5 |  | 282
|  |  | Oct |  | 66.5 | 26.5 | 55.5 |  |  | 1 |  |  |  |  | 20 |  | 169.5
|  |  | Nov |  | 71 | 24.5 | 56 |  |  | 2 |  |  |  | 6 | 14 |  | 173.5
|  |  | Dec |  | 70 | 23.5 | 69 |  |  | 4 |  |  |  | 5 | 9 |  | 180.5
|  | 2017 | Jan |  | 80 | 48 | 58.5 |  |  | 7 |  |  |  | 4 | 7 |  | 204.5
|  |  | Feb |  | 112 | 46 | 96.5 |  |  | 10.5 |  |  |  | 11.5 | 10.5 |  | 287
|  |  | Mar |  | 141 | 84 | 18 | 0.74 |  | 21.5 |  |  |  | 9 | 10 |  | 284.24
|  |  | Apr |  | 42.5 | 48.5 | 107.5 |  |  | 31 |  |  |  | 30 | 20 |  | 279.5
|  |  | May |  | 90.5 | 35.5 | 63 |  |  | 17 |  |  |  | 23.5 | 11 |  | 240.5
|  |  | Jun |  | 89 | 39.5 | 88.5 |  |  | 31.5 |  |  |  | 2.5 | 11 |  | 262
PCR303 Total |  |  |  |  | 1035 | 469 | 726 | 0.74 |  | 127.5 |  | 6 |  | 102.5 | 163 | 2 | 2631.74
PCR304 | SECURE: Support/Help Desk/Admin: Owners | 2016 | Jun |  |  | 5.5 |  |  |  | 0.5 |  | 26 |  |  |  |  | 32
|  |  | Jul |  | 6 | 11 |  |  |  | 1 |  | 49.5 |  |  | 6 |  | 73.5
|  |  | Aug |  | 3 | 10 |  |  |  | 2 |  | 14 |  |  |  |  | 29
|  |  | Sep |  | 3 | 18.5 | 17.5 |  |  | 2.5 |  |  |  | 14.5 |  |  | 56
|  |  | Oct |  | 1 | 12 | 19.5 |  |  | 1.5 |  |  |  | 3 |  |  | 37
|  |  | Nov |  | 12 | 27.5 | 15.5 |  |  | 5.5 | [6 empty] | 60.5
|  |  | Dec |  |  | 4 | 1 |  |  | 1 |  |  |  | 18 | 3 |  | 27
|  | 2017 | Jan |  |  | 7.5 | [7 empty] | 9.5 |  |  | 17
|  |  | Feb |  |  | 4.5 | 1 | [6 empty] | 30 |  |  | 35.5
|  |  | Mar |  | 5.5 | 25 |  |  |  | 5 |  |  |  | 42 |  |  | 77.5
|  |  | Apr |  |  | 15 |  |  |  | 2 |  |  |  | 2 |  |  | 19
|  |  | May |  | 0.5 | 19.5 |  |  |  | 4 |  |  |  | 2 |  |  | 26
|  |  | Jun |  |  | 16.5 |  |  |  | 2 |  |  |  | 7 |  |  | 25.5
PCR304 Total |  |  |  |  | 31 | 176.5 | 54.5 |  |  | 27 |  | 89.5 |  | 128 | 9 |  | 515.5
PCR305 | SECURE: Support/Help Desk/Admin: Partners | 2016 | Jun |  |  | 3 |  |  |  | 1 |  | 0.5 |  |  |  |  | 4.5
|  |  | Jul |  | 4.5 | 7.5 |  |  |  | 1.5 |  | 3 |  |  |  |  | 16.5
|  |  | Aug |  | 3 | 3.5 |  |  |  | 2.5 |  |  |  | 1 |  |  | 10
|  |  | Sep |  |  | 4 |  |  |  | 3 |  |  |  | 2 |  |  | 9
|  |  | Oct |  |  | 1.5 | 3 |  |  | 2.5 |  |  |  | 1.5 |  |  | 8.5
|  |  | Nov |  | 1 | 0.5 |  |  |  | 3 | [6 empty] | 4.5
|  |  | Dec |  | 1 |  |  |  |  | 1.5 |  |  |  | 10 |  |  | 12.5
|  | 2017 | Jan |  |  | 1 |  |  |  | 1.5 | [6 empty] | 2.5
|  |  | Feb |  |  | 0.5 | 1 |  |  | 2 | [6 empty] | 3.5
|  |  | Mar |  |  | 10.25 | [7 empty] | 42.5 |  |  | 52.75
|  |  | Apr |  |  | 5 | 3 | [6 empty] | 2 |  |  | 10
|  |  | May |  |  | 9 | 3 |  |  | 7.5 |  |  |  | 21.5 |  |  | 41
|  |  | Jun |  |  | 4 | 7 |  |  | 2 |  |  |  | 9.5 |  |  | 22.5
PCR305 Total |  |  |  |  | 9.5 | 49.75 | 17 |  |  | 28 |  | 3.5 |  | 90 |  |  | 197.75
PCR306 | SECURE: Support/Help Desk/Admin: Submitters | 2016 | Jun |  |  | 3.5 | 30 |  |  | 28 |  | 25 |  |  |  |  | 86.5
|  |  | Jul |  |  | 19.5 | 90.5 |  |  | 45 |  | 48 |  |  |  |  | 203
|  |  | Aug |  | 2 | 11 | 88 |  | 72 | 60 |  | 14 |  | 12.5 |  |  | 259.5
|  |  | Sep |  | 3 | 4 | 52.5 |  | 201.5 | 93.5 |  |  |  | 28 |  |  | 382.5
|  |  | Oct |  | 2 | 0.5 | 37 |  | 124 | 59 |  |  |  | 10 |  |  | 232.5
|  |  | Nov |  |  |  | 34.5 |  | 128 | 51.5 |  |  |  | 4.5 |  |  | 218.5
|  |  | Dec |  |  |  | 43 |  | 132.5 | 51 | [6 empty] | 226.5
|  | 2017 | Jan |  |  |  | 22 |  | 106.5 | 50 |  |  |  | 11.5 |  |  | 190
|  |  | Feb |  |  | 3.5 | 33 |  | 141 | 57.5 |  |  |  | 28 |  |  | 263
|  |  | Mar |  | 3 | 4.5 | 2.5 |  | 217 | 90.5 |  |  |  | 26.5 |  |  | 344
|  |  | Apr |  |  | 8.5 | 18.5 |  | 144 | 58.5 |  |  |  | 9 |  |  | 238.5
|  |  | May |  | 4 | 15 | 27.5 |  | 142 | 64.5 |  |  |  | 15.5 |  |  | 268.5
|  |  | Jun |  |  | 4.5 | 33 |  |  | 29.5 |  |  |  | 22.5 |  |  | 89.5
PCR306 Total |  |  |  |  | 14 | 74.5 | 512 |  | 1408.5 | 738.5 |  | 87 |  | 168 |  |  | 3002.5
PCR307 | SECURE: Meetings: Owners | 2016 | Jun |  |  | 2 | [5 empty] | 13.5 |  |  | 2 |  | 17.5
|  |  | Jul |  |  | 13 | [5 empty] | 7 |  |  | 5 |  | 25
|  |  | Aug |  |  | 12.5 | [5 empty] | 3 |  |  | 6 |  | 21.5
|  |  | Sep |  |  | 20.5 | [8 empty] | 3 |  | 23.5
|  |  | Oct |  |  | 22 | [8 empty] | 4 |  | 26
|  |  | Nov |  |  | 12.5 | [10 empty] | 12.5
|  |  | Dec |  |  | 9 | [8 empty] | 8 |  | 17
|  | 2017 | Jan |  |  | 32 | [8 empty] | 13 |  | 45
|  |  | Feb |  |  | 22 | [8 empty] | 11.5 |  | 33.5
|  |  | Mar |  |  | 1 | [7 empty] | 2 | 18 |  | 21
|  |  | Apr |  |  | 2.5 | [10 empty] | 2.5
|  |  | May |  |  | 13 | [10 empty] | 13
|  |  | Jun |  |  | 9 | [10 empty] | 9
PCR307 Total | [5 empty] | 171 | [5 empty] | 23.5 |  | 2 | 70.5 |  | 267
PCR308 | SECURE: Meetings: Partners | 2016 | Jun |  |  | 18.5 | [10 empty] | 18.5
|  |  | Jul |  |  | 13.5 | [5 empty] | 2 |  |  |  |  | 15.5
|  |  | Aug |  |  | 16.5 | [7 empty] | 3 |  |  | 19.5
|  |  | Sep |  |  | 23 | [7 empty] | 7 |  |  | 30
|  |  | Oct |  |  | 1.5 | [7 empty] | 2 |  |  | 3.5
|  |  | Nov |  |  | 24.5 | [7 empty] | 5 |  |  | 29.5
|  |  | Dec |  |  | 20.5 | [7 empty] | 5 |  |  | 25.5
|  | 2017 | Jan |  |  | 6.5 | [7 empty] | 12 |  |  | 18.5
|  |  | Feb |  |  | 2.5 | [10 empty] | 2.5
|  |  | Mar |  |  | 34.5 | [10 empty] | 34.5
|  |  | Apr |  |  | 2.5 | [10 empty] | 2.5
|  |  | May |  |  | 3.5 | [7 empty] | 1.5 |  |  | 5
|  |  | Jun |  |  | 19.5 | [7 empty] | 12.5 |  |  | 32
PCR308 Total | [5 empty] | 187 | [5 empty] | 2 |  | 48 |  |  | 237
PCR309 | SECURE: Meetings: Submitters | 2016 | Jun |  |  |  | 1 | [9 empty] | 1
|  |  | Jul |  |  |  | 2 |  |  |  |  | 0.5 |  |  |  |  | 2.5
|  |  | Aug |  |  | 3.5 | 2.5 | [6 empty] | 3 |  |  | 9
|  |  | Sep | [10 empty] | 5.5 |  |  | 5.5
|  |  | Oct | [10 empty] | 3 |  |  | 3
|  | 2017 | May | [10 empty] | 3 |  |  | 3
PCR309 Total | [5 empty] | 3.5 | 5.5 |  |  |  |  | 0.5 |  | 14.5 |  |  | 24
PCR310 | SECURE: Setup/Training: Owners | 2017 | May | [10 empty] | 5 |  |  | 5
PCR310 Total | [13 empty] | 5 |  |  | 5
PCR311 | SECURE: Setup/Training: Partners | 2016 | Jun |  | 3.5 | 4 | [10 empty] | 7.5
|  |  | Jul |  |  | 2 | 4 | [9 empty] | 6
|  |  | Sep |  |  | 2.5 | [10 empty] | 2.5
|  |  | Oct |  | 1 | 2 | [10 empty] | 3
|  |  | Nov |  | 2.5 | 1.5 | [10 empty] | 4
|  |  | Dec |  |  | 1.5 | [10 empty] | 1.5
|  | 2017 | Jan |  |  | 1.5 | [10 empty] | 1.5
|  |  | Feb |  |  | 2.5 | [10 empty] | 2.5
|  |  | Mar |  |  | 10.5 | [7 empty] | 5 |  |  | 15.5
|  |  | Apr |  |  | 6 | [10 empty] | 6
|  |  | May |  |  | 2.5 | 1.5 | [9 empty] | 4
|  |  | Jun |  |  | 1.5 | 8.5 | [9 empty] | 10
PCR311 Total |  |  |  |  | 7 | 38 | 14 | [6 empty] | 5 |  |  | 64
PCR312 | SECURE: Setup/Training: Submitters | 2016 | Jun |  | 3 | 0.5 | 23.5 |  |  | 16 |  | 11.5 |  |  |  |  | 54.5
|  |  | Jul |  | 2 | 7 | 25 |  |  | 24.5 |  | 14 |  |  |  |  | 72.5
|  |  | Aug |  | 4 | 9 | 17.5 |  |  | 27 |  | 2 |  |  |  |  | 59.5
|  |  | Sep |  | 2 | 10 |  |  |  | 40.5 |  |  |  | 7 |  |  | 59.5
|  |  | Oct |  | 9 | 5 |  |  |  | 30 | [6 empty] | 44
|  |  | Nov |  | 2 | 6.5 |  |  |  | 23 | [6 empty] | 31.5
|  |  | Dec |  | 2 | 9.5 |  |  |  | 26 | [6 empty] | 37.5
|  | 2017 | Jan |  | 1.5 | 6.5 | 1 |  |  | 25 | [6 empty] | 34
|  |  | Feb |  | 5 | 8 |  |  |  | 29.5 |  |  |  | 3 |  |  | 45.5
|  |  | Mar |  | 7 | 8 |  |  |  | 41.5 | [6 empty] | 56.5
|  |  | Apr |  |  | 2.5 |  |  |  | 23 | [6 empty] | 25.5
|  |  | May |  |  | 2 |  |  |  | 23.5 | [6 empty] | 25.5
|  |  | Jun |  |  | 4.5 |  |  |  | 12 | [6 empty] | 16.5
PCR312 Total |  |  |  |  | 37.5 | 79 | 67 |  |  | 341.5 |  | 27.5 |  | 10 |  |  | 562.5
PCR325 | SECURE: Support Costs | 2016 | Jul | [9 empty] | 8 |  |  |  | 8
|  |  | Aug | [9 empty] | 4 |  |  |  | 4
|  |  | Sep | [9 empty] | 2 |  |  |  | 2
PCR325 Total | [12 empty] | 14 |  |  |  | 14
Grand Total |  |  |  | 269.5 | 1759 | 1364.25 | 1415.5 | 0.74 | 1408.5 | 1262.5 | 97.5 | 242.5 | 14 | 791.25 | 251.5 | 2 | 8878.74

## S&S
Encumbrance/Expenditure Activity
OCDW PRODUCTION download as of 07/06/2017
| View: | Transaction Detail
| As of: | FY 2017 - 13 Adjustment 2017 [OPEN]
| Department: | 059
Fund | Dept | BC | Unit | Object | Sub Obj | Dept Obj | Job No | Job Description | Reference ID | Vendor Code | Vendor Name | Line Description | Doc Cd | Doc Dept | Doc ID | Rec Dt | Expenditure
12D | 059 | 12D | 3200 | 2140 |  | A100 | PCR322 | SECURE: Software |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R16-262: Economy Windows Hosting for 3 years | PRC | 001 | AP1700000019 | 2016-07-12 | 143.64
12D | 059 | 12D | 3200 | 1941 |  | A100 | PCR324 | SECURE: Professional Services | JVEAEN,059,EAUP-17000328 | VC0000010186 | LAWRENCE R HALME | R16-195: Computer Security Auditor | JVEAEN | 059 | 17000325 | 2016-07-12 | -12650 | PY
100 | 059 | 059 | 9100 | 1803 |  |  | PCR325 | SECURE: Support Costs | DO,059,16012922 | VC0000005137 | FEDERAL EXPRESS CORPORATION | EXPRESS MAIL SERVICES | PRC | 003 | 17001088 | 2016-07-14 | 9.56 | PY
12D | 059 | 12D | 3200 | 1941 | NMED | A100 | PCR324 | SECURE: Professional Services | DO,059,16018461 | VC0000010186 | LAWRENCE R HALME | R16-195: Computer Security Auditor | PRC | 003 | 17001282 | 2016-07-15 | 12650 | PY
12D | 059 | 12D | 3200 | 1941 |  | A100 | PCR324 | SECURE: Professional Services | DO,059,17012058 | VC0000010550 | SIDEPATH INC | R16-254: Security, storage, virtualization and networking projects | PRC | 003 | 17002601 | 2016-07-28 | 1550
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201606_0000139707 | JVCDS1 | 017 | FS1607280068 | 2016-07-29 | -15
100 | 059 | 059 | 9100 | 1803 |  |  | PCR325 | SECURE: Support Costs | DO,059,16012922 | VC0000005137 | FEDERAL EXPRESS CORPORATION | EXPRESS MAIL SERVICES | PRC | 003 | 17004874 | 2016-08-18 | 48.5 | PY
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17005872 | 2016-08-25 | 120.07
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201606_0000139913 | JVCDS1 | 017 | FS1608290104 | 2016-08-29 | 20.14
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201607_0000139914 | JVCDS1 | 017 | FS1608290105 | 2016-08-29 | 1242.4
12D | 059 | 12D | 3200 | 1340 |  | A100 | PCR322 | SECURE: Software |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-009: SECURE Renewal Splunk Enterprise | PRC | 001 | AP1700000286 | 2016-09-08 | 1500
12D | 059 | 12D | 3200 | 1840 |  | A100 | PCR325 | SECURE: Support Costs |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-030: Tripod Stand for SECURE Meetings | PRC | 001 | AP1700000286 | 2016-09-08 | 15.5
12D | 059 | 12D | 3200 | 2140 |  | A100 | PCR322 | SECURE: Software |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-008: Rapid 7 Nexpose Express Perpetual License Renewal R17-020: GoDaddy renewals | PRC | 001 | AP1700000286 | 2016-09-08 | 1622.69
12D | 059 | 12D | 3200 | 2200 |  | A100 | PCR324 | SECURE: Professional Services | DO,059,17014536 | VC0000015108 | NCC GROUP INC | R16-113: SOFTWARE ESCROW SERVICES | PRC | 003 | 17007697 | 2016-09-12 | 450
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17007783 | 2016-09-13 | 97.98
100 | 059 | 059 | 3200 | 2700 |  |  | PCR307 | SECURE: Meetings: Owners |  |  |  | Travel: Patrick Copland - SECURE County Meeting 3/2/16 | PREXP | 003 | 386709201600026 | 2016-09-21 | 210.02
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17008965 | 2016-09-22 | 48.99
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201608_0000140642 | JVCDS1 | 017 | FS1609290116 | 2016-09-29 | 1921.9
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17009974 | 2016-09-30 | 4.8
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201606_0000140641 | JVCDS1 | 017 | FS1609290115 | 2016-10-04 | -630.84
12D | 059 | 12D | 3200 | 2400 |  | A100 | PCR325 | SECURE: Support Costs |  | VC0000007214 | COUNTY OF ORANGE | R17-021: Hilton A/V Screen Rental 9/7/16 | GAX | 003 | AP1700000166 | 2016-10-19 | 286.55
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17012114 | 2016-10-19 | 5.77
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17012116 | 2016-10-19 | 48.74
100 | 059 | 059 | 3200 | 2601 |  |  | PCR307 | SECURE: Meetings: Owners |  |  |  | Travel: Patrick Copland - SECURE County Meeting 9/6/16 | PREXP | 003 | 387610181600026 | 2016-10-21 | 39.96
100 | 059 | 059 | 3200 | 2700 |  |  | PCR307 | SECURE: Meetings: Owners |  |  |  | Travel: Patrick Copland - SECURE County Meeting 9/6/16 | PREXP | 003 | 387610181600026 | 2016-10-21 | 145.62
12D | 059 | 12D | 3200 | 1840 |  | A100 | PCR325 | SECURE: Support Costs |  |  |  | PC/CC UseTax expense for SEP 16 NGEN Fund using 8.00% sales tax rate | JVAUD | 003 | JVUP-1700000597 | 2016-10-25 | 1.24
12D | 059 | 12D | 3200 | 1941 | NMED | A100 | PCR324 | SECURE: Professional Services | DO,059,17016020 | VC0000015979 | JAMES I WRIGHT II | R17-031: Security, support enhancement and audit remediation projects | PRC | 003 | 17012804 | 2016-10-25 | 1437.5
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201609_0000141126 | JVCDS1 | 017 | FS1610280069 | 2016-10-28 | 1276.8
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17014447 | 2016-11-08 | 6.85
12D | 059 | 12D | 3200 | 1340 |  | A100 | PCR322 | SECURE: Software |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-061: Symantec Protection Engine for Cloud Renewal R17-063: Symantec Protection Suite Enterprise Renewal | PRC | 001 | AP1700000433 | 2016-11-09 | 1950
12D | 059 | 12D | 3200 | 1840 |  | A100 | PCR323 | SECURE: Hardware |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-064: SECURE Computer Parts | PRC | 001 | AP1700000433 | 2016-11-09 | 629.97
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17015286 | 2016-11-16 | 5.93
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201610_0000141308 | JVCDS1 | 017 | FS1611280069 | 2016-11-28 | 1276.8
12D | 059 | 12D | 3200 | 1341 |  | A100 | PCR323 | SECURE: Hardware | PO,059,17010850 | VC0000010287 | CDW LLC | R17-082: Servers HPE Foundation Care | PRC | 003 | 17016544 | 2016-12-01 | 6196.32
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17016873 | 2016-12-05 | 5.93
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17016876 | 2016-12-05 | 61.36
12D | 059 | 12D | 3200 | 2140 |  | A100 | PCR322 | SECURE: Software |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-091: Annual WordPress.com Support Plan | PRC | 001 | AP1700000540 | 2016-12-13 | 35.88
12D | 059 | 12D | 3200 | 1340 |  | A100 | PCR321 | SECURE: LA County Software Maintenance | DO,059,17017181 | VC0000007206 | COUNTY OF LOS ANGELES | R17-006: FY 2016-17 | PRC | 003 | 17018181 | 2016-12-14 | 770000
12D | 059 | 12D | 3200 | 1840 |  | A100 | PCR323 | SECURE: Hardware |  |  |  | PC/CC UseTax expense for NOV 16 NGEN Fund using 8.00% sales tax rate | JVAUD | 003 | JVUP-1700000990 | 2016-12-20 | 2.79
12D | 059 | 12D | 3200 | 1340 |  | A100 | PCR321 | SECURE: LA County Software Maintenance | PO,059,17011010 | VC0000010287 | CDW LLC | R17-114: VMware Support License for SECURE | PRC | 003 | 17019209 | 2016-12-23 | 8321
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201611_0000141951 | JVCDS1 | 017 | FS1612290067 | 2016-12-29 | 1276.8
12D | 059 | 12D | 3200 | 1340 |  | A100 | PCR321 | SECURE: LA County Software Maintenance |  |  |  | R17-114: VMware Support License for SECURE | JVJC | 059 | 17000275 | 2016-12-30 | -8321
12D | 059 | 12D | 3200 | 1340 |  | A100 | PCR322 | SECURE: Software |  |  |  | R17-114: VMware Support License for SECURE | JVJC | 059 | 17000275 | 2016-12-30 | 8321
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17020221 | 2017-01-05 | 49.23
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17020223 | 2017-01-05 | 5.83
12D | 059 | 12D | 3200 | 1341 |  | A100 | PCR323 | SECURE: Hardware |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-112: HP Network Switch Support Renewal | PRC | 001 | AP1700000653 | 2017-01-06 | 720
12D | 059 | 12D | 3200 | 2140 |  | A100 | PCR322 | SECURE: Software |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-109: Business Email Services R17-100: SurveyMonkey Renewal | PRC | 001 | AP1700000653 | 2017-01-06 | 252.58
12D | 059 | 12D | 3200 | 2700 |  | A100 | PCR308 | SECURE: Meetings: Partners |  | VC0000013927 | US BANK NATIONAL ASSOCIATION ND | R17-108: SECURE Partner Meeting at CRAC (Reimbursement of $884 received from Counties) | PRC | 001 | AP1700000654 | 2017-01-06 | 1019.73
12D | 059 | 12D | 3200 | 1941 | NMED | A100 | PCR324 | SECURE: Professional Services | DO,059,17016020 | VC0000015979 | JAMES I WRIGHT II | R17-031: Security, support enhancement and audit remediation projects | PRC | 003 | 17020772 | 2017-01-11 | 625
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17020972 | 2017-01-12 | 14.74
12D | 059 | 12D | 3200 | 1340 |  | A100 | PCR322 | SECURE: Software | PO,059,17011104 | VC0000001266 | SHI INTERNATIONAL CORP | R17-089: CimTrak System Change Monitoring (SECURE) | PRC | 003 | 17020990 | 2017-01-12 | 2406.27
12D | 059 | 12D | 3200 | 2140 |  | A100 | PCR322 | SECURE: Software | PO,059,17011104 | VC0000001266 | SHI INTERNATIONAL CORP | R17-089: CimTrak System Change Monitoring (SECURE) | PRC | 003 | 17020990 | 2017-01-12 | 12030.91
12D | 059 | 12D | 3200 | 1341 |  | A100 | PCR323 | SECURE: Hardware | PO,059,17011107 | VC0000010287 | CDW LLC | R17-123: Renew HP 3PAR SAN Hardware Maintenance/Support | PRC | 003 | 17020923 | 2017-01-17 | 8343.59
12D | 059 | 12D | 3200 | 1341 |  | A100 | PCR323 | SECURE: Hardware | PO,059,17011065 | VC0000010550 | SIDEPATH INC | R17-120: Brocade support for VDX6740-24 Port | PRC | 003 | 17021384 | 2017-01-18 | 2668
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201612_0000142368 | JVCDS1 | 017 | FS1701270066 | 2017-01-27 | 1276.8
12D | 059 | 12D | 3200 | 1941 |  | A100 | PCR324 | SECURE: Professional Services | DO,059,17012058 | VC0000010550 | SIDEPATH INC | R16-254: Security, storage, virtualization and networking projects | PRC | 003 | 17022681 | 2017-01-31 | 3150
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17022865 | 2017-02-02 | 11.92
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17022881 | 2017-02-02 | 9.58
12D | 059 | 12D | 3200 | 1840 |  | A100 | PCR323 | SECURE: Hardware |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-149: Microphone and Speaker | PRC | 001 | AP1700000769 | 2017-02-09 | 999
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17024016 | 2017-02-14 | 10.31
12D | 059 | 12D | 3200 | 1840 |  | A100 | PCR323 | SECURE: Hardware |  |  |  | PC/CC UseTax expense for JAN 17 NGEN Fund using 7.75% sales tax rate | JVAUD | 003 | JVUP-1700001333 | 2017-02-22 | 77.42
12D | 059 | 12D | 3200 | 1340 |  | A100 | PCR322 | SECURE: Software | DO,059,17018811 | VC0000010287 | CDW LLC | R17-126: F5 BIG-IP Support | PRC | 003 | 17025200 | 2017-02-24 | 26010
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201701_0000142797 | JVCDS1 | 017 | FS1702250070 | 2017-02-27 | 1276.8
12D | 059 | 12D | 3200 | 1800 |  | A100 | PCR325 | SECURE: Support Costs |  |  |  | R17-002: Office Supplies Unit 3200 | JVJC | 059 | 17000363 | 2017-02-28 | 28.61
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17025829 | 2017-03-01 | 68.07
12D | 059 | 12D | 3200 | 2200 |  | A100 | PCR324 | SECURE: Professional Services | DO,059,17019945 | VC0000015108 | NCC GROUP INC | R17-011: SOFTWARE ESCROW SERVICES | PRC | 003 | 17026124 | 2017-03-03 | 2250
12D | 059 | 12D | 3200 | 1840 |  | A100 | PCR323 | SECURE: Hardware |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-149: Yamaha Microphone | PRC | 001 | AP1700000861 | 2017-03-08 | 297.9
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17027949 | 2017-03-20 | 6.12
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17027952 | 2017-03-20 | 42.28
12D | 059 | 12D | 3200 | 2200 |  | A100 | PCR324 | SECURE: Professional Services | DO,059,17020105 | VC0000015108 | NCC GROUP INC | R17-011: SOFTWARE ESCROW SERVICES | PRC | 003 | 17028189 | 2017-03-21 | 150
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201702_0000143008 | JVCDS1 | 017 | FS1703280069 | 2017-03-30 | 1276.8
12D | 059 | 12D | 3200 | 1800 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17010348 | VC0000007447 | STAPLES CONTRACT & COMMERCIAL INC | R17-002: OFFICE SUPPLIES UNIT 3200 | PRI | 003 | 201703253334432743 | 2017-04-06 | 40.51
12D | 059 | 12D | 3200 | 1341 |  | A100 | PCR323 | SECURE: Hardware |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-181: APC KVM Extended Warranty | PRC | 001 | AP1700000970 | 2017-04-07 | 453
12D | 059 | 12D | 3200 | 2140 |  | A100 | PCR322 | SECURE: Software |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-177: GoToMeeting Service Accounts R17-192: Hard Disk Erasure Software Tool | PRC | 001 | AP1700000970 | 2017-04-07 | 1887.17
12D | 059 | 12D | 3200 | 2140 |  | A100 | PCR322 | SECURE: Software | DO,059,17021013 | VC0000002937 | INSIGHT PUBLIC SECTOR INC | R17-147: Microsoft Enterprise Licenses | PRC | 003 | 17030744 | 2017-04-13 | 26146.8
12D | 059 | 12D | 3200 | 1340 |  | A100 | PCR322 | SECURE: Software | PO,059,17011572 | VC0000010287 | CDW LLC | R17-180: Veeam Support for SECURE | PRC | 003 | 17031150 | 2017-04-18 | 6216
100 | 059 | 059 | 3200 | 2700 |  |  | PCR307 | SECURE: Meetings: Owners |  |  |  | Travel: Patrick Copland - SECURE County Meeting 12/13/16 | PREXP | 003 | 394404181700025 | 2017-04-21 | 103.52
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201703_0000143717 | JVCDS1 | 017 | FS1704260069 | 2017-04-26 | 1276.8
12D | 059 | 12D | 3200 | 2700 |  | A100 | PCR307 | SECURE: Meetings: Owners |  | VC0000007214 | COUNTY OF ORANGE | SECURE Owners Meeting 4/5/2017 | GAX | 003 | 17007545 | 2017-05-03 | 101.83
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17033366 | 2017-05-09 | 7.23
12D | 059 | 12D | 3200 | 1340 |  | A100 | PCR322 | SECURE: Software |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-203: Cerberus FTP Server Support and Maint | PRC | 001 | AP1700001052 | 2017-05-09 | 450
12D | 059 | 12D | 3200 | 2140 |  | A100 | PCR322 | SECURE: Software |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-202: Digicert Code Signing Digital Certificate R17-217: GoDaddy Business E-mail | PRC | 001 | AP1700001052 | 2017-05-09 | 606.88
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17034524 | 2017-05-18 | 51.64
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201704_0000144176 | JVCDS1 | 017 | FS1705250070 | 2017-05-25 | 1307.01
12D | 059 | 12D | 3200 | 1800 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17010301 | VC0000004802 | OFFICE DEPOT INC | R17-001: OFFICE SUPPLIES UNIT 3200 | PRI | 003 | EC1705010265 | 2017-05-25 | 140.12
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17036016 | 2017-06-01 | 25.89
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17036825 | 2017-06-09 | 8.57
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | 17036830 | 2017-06-09 | 13.66
12D | 059 | 12D | 3200 | 1340 |  | A100 | PCR322 | SECURE: Software | PO,059,17011647 | VC0000012364 | ESECURITY SOLUTIONS LLC | R17-189: SAFENET SAS-CLOUD | PRC | 003 | 17036991 | 2017-06-12 | 26392.5
12D | 059 | 12D | 3200 | 1800 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17010348 | VC0000007447 | STAPLES CONTRACT & COMMERCIAL INC | R17-002: OFFICE SUPPLIES UNIT 3200 | PRI | 003 | 201706103342711441 | 2017-06-13 | 53.17
12D | 059 | 12D | 3200 | 1840 |  | A100 | PCR323 | SECURE: Hardware |  | VC0000003134 | US BANK NATIONAL ASSOCIATION ND | R17-237: HP LightScribe CD-R and DVD-R | PRC | 001 | AP1700001162 | 2017-06-14 | 254.41
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201705_0000145008 | JVCDS1 | 017 | FS1706280068 | 2017-06-28 | 1286.87
12D | 059 | 12D | 3200 | 1941 |  | A100 | PCR324 | SECURE: Professional Services | CT,059,17010907 | VC0000012364 | ESECURITY SOLUTIONS LLC | R17-152: Web Application Penetration Test | PRC | 003 | 17039069 | 2017-06-28 | 5250
12D | 059 | 12D | 3200 | 1941 | NMED | A100 | PCR324 | SECURE: Professional Services | DO,059,17023740 | VC0000010186 | LAWRENCE R HALME | R16-195: SECURE System Auditor Services | PRC | 003 | 17039124 | 2017-06-28 | 7420
12D | 059 | 12D | 3200 | 1941 | NMED | A100 | PCR324 | SECURE: Professional Services | CT,059,17010160 | VC0000010186 | LAWRENCE R HALME | R17-037: SECURE System Auditor Services | PRC | 003 | 17039128 | 2017-06-28 | 20250
12D | 059 | 12D | 3200 | 1940 |  | A100 | PCR326 | SECURE: OCIT Charges |  |  |  | CEOIT_ER01A000_CEOIT-ER01A-201706_0000145202 | JVCDS1 | 017 | FS1706290068 | 2017-06-29 | 1286.87
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | AP1800000052 | 2017-07-05 | 13.26
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | AP1800000051 | 2017-07-05 | 14.23
12D | 059 | 12D | 3200 | 1803 |  | A100 | PCR325 | SECURE: Support Costs | DO,059,17013218 | VC0000005137 | FEDERAL EXPRESS CORPORATION | FEDEX CONVENIENCE | PRC | 003 | AP1800000053 | 2017-07-06 | 6.06
967513.65
[15 empty] | OC Data Center Charges | PCR326 | 15356.95
[15 empty] | Meetings: Owners | PCR307 | 600.95
[15 empty] | Meetings: Partners | PCR308 | 1019.73
[15 empty] | Meetings: Submitters | PCR309 | 0
[15 empty] | Digital Tokens | PCR320 | 0
[15 empty] | LA County Software Maintenance | PCR321 | 770000
[15 empty] | Software | PCR322 | 115972.32
[15 empty] | Hardware | PCR323 | 20642.4
[15 empty] | Professional Services | PCR324 | 42532.5
[15 empty] | OC Admin Support Costs | PCR325 | 1388.8
967513.65

## Revenue
Revenue Activity
OCDW PRODUCTION download as of 07/06/2017
| View: | Transaction Detail
| From Period: | FY 2017 - 01 July 2016 [CLOSED]
| To Period: | FY 2017 - 13 Adjustment 2017 [OPEN]
| Department: | 059
Fund | Dept | BC | Unit | RSRC | Dept RSRC | Job | Job Description | Line Description | Doc Cd | Doc Dept | Doc ID | Rec Dt | Revenue
12D | 059 | 12D | 3200 | 7590 | M100 | PCR331 | SECURE: Revenue: Partners | SECURE County Pymt - San Mateo County - Invoice #SM2016 | CR | 059 | 17000705 | 2016-07-14 | -25000
12D | 059 | 12D | 3200 | 7590 | M100 | PCR331 | SECURE: Revenue: Partners | San Mateo County SECURE Invoice #SM2016 | JVYE | 059 | 17000975 | 2016-07-25 | 25000
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17003371 | 2016-08-31 | -100
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17003373 | 2016-08-31 | -100
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17004677 | 2016-09-20 | -100
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17004681 | 2016-09-20 | -300
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17005346 | 2016-09-30 | -100
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17007794 | 2016-11-10 | -100
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17008207 | 2016-11-17 | -100
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17008209 | 2016-11-17 | -200
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17009992 | 2016-12-20 | -200
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17010905 | 2017-01-05 | -100
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17011387 | 2017-01-13 | -100
12D | 059 | 12D | 3200 | 7670 | A100 | PCR308 | SECURE: Meetings: Partners | R17-108: SECURE Partner Meeting at CRAC (Reimbursement of $884 received from Counties) | CR | 059 | 17011509 | 2017-01-17 | -884
12D | 059 | 12D | 3200 | 7590 | M100 | PCR331 | SECURE: Revenue: Partners | SECURE County Pymt - Santa Barbara County - Invoice #SB2017 | CR | 059 | 17011799 | 2017-01-20 | -10000
12D | 059 | 12D | 3200 | 7590 | M100 | PCR331 | SECURE: Revenue: Partners | SECURE County Pymt - Sacramento County - Invoice #SA2017 | CR | 059 | 17012259 | 2017-01-30 | -50000
12D | 059 | 12D | 3200 | 7590 | M100 | PCR331 | SECURE: Revenue: Partners | SECURE County Pymt - Marin County - Invoice #MC2017 | CR | 059 | 17012261 | 2017-01-30 | -10000
12D | 059 | 12D | 3200 | 7130 | M100 | PCR330 | SECURE: Revenue: Owners | SECURE County Pymt - Los Angeles County - Invoice #LA2017 | CR | 059 | 17012703 | 2017-02-06 | -292500
12D | 059 | 12D | 3200 | 7130 | M100 | PCR330 | SECURE: Revenue: Owners | SECURE County Pymt - San Diego County - Invoice #SD2017 | CR | 059 | 17012897 | 2017-02-08 | -292500
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17013171 | 2017-02-14 | -200
12D | 059 | 12D | 3200 | 7130 | M100 | PCR330 | SECURE: Revenue: Owners | SECURE County Pymt - Riverside County - Invoice #RV2017 | CR | 059 | 17013729 | 2017-02-24 | -292500
12D | 059 | 12D | 3200 | 7590 | M100 | PCR331 | SECURE: Revenue: Partners | SECURE County Pymt - Ventura County - Invoice #VN2017 | CR | 059 | 17013862 | 2017-02-27 | -25000
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17013921 | 2017-02-28 | -200
12D | 059 | 12D | 3200 | 7590 | M100 | PCR331 | SECURE: Revenue: Partners | SECURE County Pymt - San Mateo County - Invoice #SM2017 | CR | 059 | 17016346 | 2017-04-10 | -25000
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17019012 | 2017-05-25 | -500
12D | 059 | 12D | 3200 | 7470 | A100 | PCR320 | SECURE: Digital Tokens | SECURE DIGITAL TOKENS | CR | 059 | 17019291 | 2017-05-30 | -200
-1000984
[11 empty] | Meetings | PCR308 | -884
[11 empty] | Digital Tokens | PCR320 | -2600
[11 empty] | Revenue: Owners | PCR330 | -877500
[11 empty] | Revenue: Partners | PCR331 | -120000
-1000984